## User Acceptance Testing
Project Name: | User Acceptance Testing webportal SKYBOT
Customer/User: | John Doe
Lead Developer: | Oleh Moroz
Lead QA/Tester: | Oleh Moroz
Release Date: | 2024-02-14
Item | Acceptance Criteria or Requirement | Test Type | Owner | Priority | Test Result | Test Date | Comments
1 | As a potential client, I want successfully open the website main page with electric scooters, for future purchase | Functional | Mariia Mielnikova | High | Pass | 2024-02-02 | Test is successful
2 | As a non registered User, I want to sign in with email on the SKYBOT page, for access to personal options | Registration and Login | Mariia Mielnikova | High | Pass | 2024-02-02 | Test passed. User is successfully registered
3 | As a non registered User, I want to sign in with Facebook on the SKYBOT page, for access to personal options | Registration and Login | Mariia Mielnikova | High | Pass | 2024-02-02 | Test passed. User is successfully registered
4 | As a non registred User, I want to sign in with Google Account on the SKYBOT page, for access to personal options | Registration and Login | Mariia Mielnikova | High | Partial Passed | 2024-02-02 | Test is partially passed. There is problem with interconnection two platforms. User didn't have options to choose profiles Google account, but registration is successful
5 | As a registered User I want to log in to my profile on the SKYBOT page with email, to have option become a Member in the future | Registration and Login | Mariia Mielnikova | High | Pass | 2024-02-02 | Test passed. User is successfully login
8 | As a fan of the Skybot Extreamer I want to read technical information and see photos on the SKYBOT page | Reflection | Mariia Mielnikova | High | Pass | 2024-02-02 | Test passed. All information about Skybot Extreamer is available and visible
9 | As a new Member I want to use Contact Us form to send question about section “My Rewards” | Functional | Mariia Mielnikova | High | Pass | 2024-02-03 | Test passed. But in this section is presented problems with translating (language issues)
10 | As a new visitor of the page, I want interact with Chat box, to ask quick question about delivery and recieve answer | Functional | Mariia Mielnikova | High | Fail | 2024-02-04 | Test is failed. There is no response from support team
11 | As a parent, I want to have option to choose something for my 10 year-old child, so I can add it to the cart | Functional | Mariia Mielnikova | High | Pass | 2024-02-04 | Test is passed. User have variety of products.For different age groups, sizes. Also products could be added to cart
12 | As a non registered User, I want to have option to interact with my cart, so that I could buy items from it | Functional | Mariia Mielnikova | High | Partial Passed/Blocked | 2024-02-04 | Test is partially passed. There is problem with delivery (delivery must be paid, but on the website it is free for all options). Also I can't test payment options
13 | As a registered User, I want to have opportunity to delete items from my cart, so that i could add new items to it | Functional | Mariia Mielnikova | High | Partial Passed | 2024-02-04 | Test is partially passed. There is problem with adding items from the main page by clicking directly to button "Add to the cart"
14 | As a registered User, I want to leave review on a Skybot Dualtron, so that it will help future customers make a decision | Functional | Mariia Mielnikova | High | Pass | 2024-02-04 | Test passed. User could leave the review
15 | As a registered User, I want to change my review on a Skybot Dualtron, so that I could change my opinion after using it for a while. | Functional | Mariia Mielnikova | High | Pass | 2024-02-04 | Test passed. User could edit his/her own review
16 | As a registered User, I want to delete my review on a Skybot Dualtron, so that I could change rate for this item | Functional | Mariia Mielnikova | High | Pass | 2024-02-04 | Test passed. User could delete his/her own review
17 | As a non-registered User, I want to sign up for the first ride, so that I could choose type of the scooter in the future | Functional | Mariia Mielnikova | High | Partial Passed/Blocked | 2024-02-04 | Test is partially passed. In this moment we have blocked optons to sign up
18 | As a new User (registered and log in), I want to watch video about Cheapest scooters, so that I could pick one of them and buy it | Functional | Mariia Mielnikova | Medium | Pass | 2024-02-04 | Test passed. User could ineract with videos
19 | As a registered and log in User, I want to change the option “Profile Visibility”. so that anybody could disturb me and my profile will be private | Functional | Mariia Mielnikova | Low | Pass | 2024-02-04 | Test passed. User could change the visibility of the profile
20 | As a registered and log in User, I want to become a member of the SKYBOT, so that i could chat with other people and share my experience with them | Functional | Mariia Mielnikova | High | Pass | 2024-02-04 | Test passed. But in this section is presented problems with translating (language issues)
21 | As a registered User, I want to use option “Forgot my password”, so that I could change my password if I forgot it | Functional | Mariia Mielnikova | High | Pass | 2024-02-04 | Test passed. Users could use the option "Forgot password" and receive a link to reset the password.

## US 1
ACCEPTANCE CRITERIA | As a potential client, I want successfully open the website main page with electric scooters, for future purchase
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 1
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT portal opening without any delays and errors. All elements loading quick
2. Verify the page load time and extra elements

## US 2
ACCEPTANCE CRITERIA | As a non registred User, I want to sign in with email on the SKYBOT page, for access to personal options
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 2
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | Registration on the web portal SKYBOT is succesfull
2. Click on the button "Log in" |  | All text is visible and could be edited
3. Pick option "Sign Up with Email" |  | All buttons are active
4. Write Your email address and password |  | User had personal profile
5. Approve that You are not robot and give "Sign Up"
6. Click "Sign Up"

## US 3
ACCEPTANCE CRITERIA | As a non registred User, I want to sign in with Facebook on the SKYBOT page, for access to personal options
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 3
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | Registration on the web portal SKYBOT is succesfull
2. Click on the button "Log in" |  | All buttons are active
3. Pick option "Sign Up with Facebook" |  | All data from Facebook account is correct and relevant
4. Wait until system requests access to the Users data from Facebook account |  | Photo from Facebook also available on the SKYBOT website
5. Confirm Your profile
6. Wait reloading page

## US 4
ACCEPTANCE CRITERIA | As a non registred User, I want to sign in with Google Account on the SKYBOT page, for access to personal options
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 4
STATUS | Partial Passed
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | Registration on the web portal SKYBOT is succesfull
2. Click on the button "Log in" |  | All buttons are active
3. Pick option "Sign Up with Google" |  | All data from Google account is correct and relevant
4. Wait until system requests access to the Users data from Google account |  | Photo from Google also available on the SKYBOT website
5. Confirm Your profile |  | When SKYBOT try to connect with Google, User see a window with suggested profiles
6. Wait reloading page

## US 5
ACCEPTANCE CRITERIA | As a registered User I want to log in to my profile on the SKYBOT page with email, to have option become a Member in the future
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 5
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | Login on the web portal SKYBOT is succesfull
2. Click on the button "Log in" |  | All buttons are active
3. Click option "Already a member?Log In" |  | All text is visible and could be edited
4. Pick "Log in with Email"
5. Insert email and password, which were used during the registration
6. Click "Log in"
7. Wait until page is reload

## US 8
ACCEPTANCE CRITERIA | As a fan of the Skybot Extreamer I want to read technical information and see photos on the SKYBOT page
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 8
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Scroll down to the popular products |  | All buttons are active
3. On the active menu find and open page with Skybot Extreamer |  | All information about Skybot Extreamer is available and visible
4. Explore page with Skybot Extreamer (photos, technical description, reviews) |  | Photos have good scalability and good quality

## US 9
ACCEPTANCE CRITERIA | As a new Member I want to use Contact Us form to send question about section “My Rewards”
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 9
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Click on the button "Log in" |  | All buttons are active
3. Click option "Already a member?Log In" |  | Login on the web portal SKYBOT is succesfull
4. Pick "Log in with Email" |  | The page loads without delays and errors
5. Insert email and password, which were used during the registration and click "Log in" |  | Text is visible and could be edited
6. After page is reload, scroll down to the section "Contact Us" |  | User recieve confirmation notification, that message was sent
7. Fill out all blank lines with Your relevant data (name, address, phone and email)
8. In the line "Topic" write - My rewards
9. In the line "Message" write - I would like to ask You, what type of rewards did we get and for what purposes?
10. Click "Надіслати"
11. As a confirmation notification You see "Дякуємо, що заповнили форму."

## US 10
ACCEPTANCE CRITERIA | As a new visitor of the page, I want interact with Chat box, to ask quick question about delivery and recieve answer
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 10
STATUS | FAIL
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Wait until appears icon "Let's Chat" in the right lower corner |  | All buttons are active
3. Click it and wait untill window opens |  | The page loads without delays and errors
4. Write question “Hello! How much will delivery to Spain cost?” and click "Send" |  | Text is visible and could be edited
5. Recieve as answer special form |  | Chat Box easelly opens and closes
6. Fill it out and send |  | Response is quick
7. Recieve confirmation that Your message was succesfully sent

## US 11
ACCEPTANCE CRITERIA | As a parent, I want to have option to choose something for my 10 year-old child, so I can add it to the cart
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 11
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Scroll down to the section with popular items |  | The page loads without delays and errors
3. Switch products by using special pointers |  | Active menu with items works correctly
4. Pick model Skybot Child Scooter, with information "Exclusively for children" |  | Page with product opens without delays and errors
5. Read all description |  | Technical description and photos are visible
6. Pick color and add to the cart |  | Options with color is active and could be switchable
7. Wait until appears side bar with information about Your cart |  | All buttons are active and could be used
8. Verify all information that presented |  | Cart is displayed properly

## US 12
ACCEPTANCE CRITERIA | As a non registered User, I want to have option to interact with my cart, so that I could buy items from it
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 12
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Scroll down to the section with popular items |  | All buttons are active
3. Pick model Skybot Child Scooter, with information "Exclusively for children" |  | All information about Skybot Child Scooter is available and visible
4. Choose white color and add it to the cart |  | Photos have good scalability and good quality
5. Click option "View cart" |  | Color option is active and could be changed
6. Change quantity from 1 for 3 |  | Page with cart opens without any delays and errors
7. Add note “Hello! Leave it on the yard, please” |  | Quantity of the items could be change
8. Check the correctness of calculations after adding products |  | Line for the promocode is visible and clickable
9. Verify the correctness of delivery price |  | User could interact with note option
10. Press the button "Checkout" and continue with payment |  | User could choose delivery option

## US 13
ACCEPTANCE CRITERIA | As a registered User, I want to have opportunity to delete items from my cart, so that i could add new items to it
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 13
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Click on the button "Log in" |  | Login to your account is successful and without errors
3. Pick "Log in with Email" (Insert email and password, which were used during the registration) |  | Adding items to the cart from the main page is successful
4. Scroll down to the section with popular items |  | Page with cart opens without any delays and errors
5. Choose models - Skybot Day-to-day, Skybot Extreamer, Skybot Dualtron and add it to Your cart |  | Quantity of all added earlier items is correct
6. Open Your cart and check all items in it |  | All buttons is active and clickable
7. Delete each items by clicking on special sign "X" near products |  | After deleting items they dissapear from cart
8. After deleting all product, cart is empty and You see the link “Continue browsing” |  | Link “Continue browsing” is active

## US 14
ACCEPTANCE CRITERIA | As a registered User, I want to leave review on a Skybot Dualtron, so that it will help future customers make a decision
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 14
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Click on the button "Log in" |  | All buttons are active
3. Pick "Log in with Email" (Insert email and password, which were used during the registration) |  | Login to your account is successful and without errors
4. Scroll down to the section with popular items |  | Page with Skybot Dualtron is opening without any delays and is active
5. Choose item - Skybot Dualtron and open |  | All elements of the page is active
6. Scroll down to the section with reviews |  | Text is visible is could be edited
7. Click on the button "Leave review" and interact with new lines |  | User could add photo to the review
8. Rate this item, write the title and the review, add photo |  | User couldn't publish review if all fields are not filled in
9. Click "Publish" |  | After publishing, review is presented on the page and don't disappear
10. Wait for your feedback to be processed

## US 15
ACCEPTANCE CRITERIA | As a registered User, I want to change my review on a Skybot Dualtron, so that I could change my opinion after using it for a while.
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 15
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Click on the button "Log in" |  | All buttons are active
3. Pick "Log in with Email" (Insert email and password, which were used during the registration) |  | Login to your account is successful and without errors
4. Scroll down to the section with popular items |  | Page with Skybot Dualtron is opening without any delays and is active
5. Choose item - Skybot Dualtron and open |  | All elements of the page is active
6. Scroll down to the section with reviews |  | Text is visible is could be edited
7. Click on the button "See your review" |  | User could add new photo to the review (but not more than 3)
8. After your review is highlighted, click on three dots and choose option "Edit review" |  | User couldn't publish review if all fields are not filled in
9. Change title "Amazing scooter (use it for a month)" and click "Update" |  | After editing, review is presented on the page and don't disappear
10. After updating, You see notification "Review updated" |  | After updating User see notification "Review updated"

## US 16
ACCEPTANCE CRITERIA | As a registered User, I want to delete my review on a Skybot Dualtron, so that I could change rate for this item
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 16
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Click on the button "Log in" |  | All buttons are active
3. Pick "Log in with Email" (Insert email and password, which were used during the registration) |  | Login to your account is successful and without errors
4. Scroll down to the section with popular items |  | Page with Skybot Dualtron is opening without any delays and is active
5. Choose item - Skybot Dualtron and open |  | All elements of the page is active
6. Scroll down to the section with reviews |  | After deleting the review it disappear
7. Click on the button "See your review" |  | After deleting the review User see notification "Review deleted"
8. After your review is highlighted, click on three dots and choose option "Delete review"
9. Confirm Your action by click "Delete"
10. After deleting, see confirmation "Review deleted" and re-check

## US 17
ACCEPTANCE CRITERIA | As a non-registered User, I want to sign up for the first ride, so that I could choose type of the scooter in the future
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 17
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Click on the Main menu button "Our services" |  | All buttons are active
3. After new page is opens, scroll down to section "Electric scooter first ride" |  | "Our services" page opens without any delays and is active
4. Click on the option "Book now" |  | User could registrate to the first ride
5. Fill out all needed data (name, email and phone to the contact) and confirm Your action |  | User see confirmation after successful operation

## US 18
ACCEPTANCE CRITERIA | As a new User (registered and log in), I want to watch video about Cheapest scooters, so that I could pick one of them and buy it
PRIORITY | Medium
CREATED BY | Mariia Mielnikova
USER STORY | 18
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Click on the button "Log in" |  | All buttons are active
3. Pick "Log in with Email" (Insert email and password, which were used during the registration) |  | Login to your account is successful and without errors
4. On the main top menu click on the "Video reviews" |  | "Video reviews" page opens without any delays and is active
5. On the new page with videos, scroll down to the video "Top 5 Best Cheap Scooters 2023! - We Tested Them All!" |  | All actions that are available during viewing are possible and work correctly
6. Play it and try to use different option (play, pause, spin, change scalability, mute)

## US 19
ACCEPTANCE CRITERIA | As a registered and log in User, I want to change the option “Profile Visibility”. so that anybody could disturb me and my profile will be private
PRIORITY | Low
CREATED BY | Mariia Mielnikova
USER STORY | 19
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Click on the button "Log in" |  | All buttons are active
3. Pick "Log in with Email" (Insert email and password, which were used during the registration) |  | Login to your account is successful and without errors
4. After You login, open main menu of Your profile (right top corner, avatar icon or Your photo) |  | Main profile menu is active, visible and could be used
5. Click option "My account" |  | "My account" page has all valid information about User
6. After Your profile information is loading, scroll down to the section "Profile visibility" |  | Function "Profile visibility" could be change in both sides in any time
7. Click option "Make profile private" |  | User will recieve notification "Profile privacy updated successfully"
8. Confirm Your actions
9. Read notification "Profile privacy updated successfully"

## US 20
ACCEPTANCE CRITERIA | As a registered and log in User, I want to become a member of the SKYBOT, so that i could chat with other people and share my experience with them
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 20
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Click on the button "Log in" |  | All buttons are active
3. Pick "Log in with Email" (Insert email and password, which were used during the registration) |  | Login to your account is successful and without errors
4. Scroll down to the section "Група Skybot" |  | Button "Request to join" is active and clickable
5. Click to the button "Request to join" |  | After accepting, User see notification "You've requested to join Група Skybot."
6. Confirm Your actions to join the group
7. Read notification "You've requested to join Група Skybot."

## US 21
ACCEPTANCE CRITERIA | As a registered User, I want to use option “Forgot my password”, so that I could change my password if I forgot it
PRIORITY | High
CREATED BY | Mariia Mielnikova
USER STORY | 21
STATUS | PASS
STEPS TO REPRODUSE FOR UAT: |  | EXPECTED RESULTS:
1. Visit web portal - https://prometheusqastage3.wixsite.com/skybot |  | SKYBOT is opening without any delays and is active
2. Click on the button "Log in" |  | All buttons are active
3. Pick "Log in with Email" |  | Function "Forgot my password" is working properly
4. Click on the button "Forgot my password" |  | Link for email sending quick and without errors
5. Insert Your email, which You give during the registration |  | After changing, User will use the last one password
6. Click "Reset password"
7. After You will recieve link, reset Your password and save it for future